## Project Dashboard
BALLYS AI R&D — PROJECT DASHBOARD
Last Updated: 2026-04-14 |  |  | P0: 5 ¦ P1: 4 ¦ P2: 4 ¦ P3: 1 |  |  | Open GitLab Issues (Frank): 10
# | Project | Priority | Status | Criticality | GitLab Issues | Next Due Date | PIT Status | Production URL | Tech Stack | Next Action | Owner
1 | Hackathon Platform | P0 | Production | High | 2 open (#13, #14) | 2026-04-17 | SSO Done, DNS Done, NOT in My App | https://hackathon.ballys.com | React 18, FastAPI, PostgreSQL, Gemini | Migrate to scalable infra (due Apr 17) | Frank Enendu
2 | Game Experience Profile | P0 | Active | Low | 2 open (#11, #12) | 2026-04-16 | Nothing done | https://main.d2igua90qmin6r.amplifyapp.com | Python, Gemini 3 Flash, YouTube API | Decompress dimensions 9→5/6 (due Apr 16) | Frank Enendu
3 | Portfolio Optimisation Agent | P0 | Planning | Medium | 1 open (#16) | 2026-04-25 | N/A | - | TBD | Start brainstorming (due Apr 25) | Frank Enendu
4 | R&D Prototype SSO/DNS | P0 | Blocked | High | 1 open (#15) | 2026-04-20 | All prototypes pending | - | PIT / Infrastructure | Follow up SSO & DNS for all prototypes (due Apr 20) | Frank Enendu
5 | Conference Write-Up | P1 | In Progress (69%) | Medium | 2 open (#29, #30) | 2026-04-17 | N/A | - | GitLab Pages | Review conference update #30 (due Apr 17) | Frank + Al
6 | Ballys Skills Repo | P1 | Active Dev | Medium | 0 (skills repo) | - | DNS ticket raised, no SSO | - | Claude Code Skills, GitLab Pages | Skills Repo Promotion brainstorm (Apr 16) | Frank Enendu
7 | Capex Machine | P1 | Planning Complete | Low | 0 (closed #18) | - | SSO done, no DNS/cert | - | FastAPI, Bedrock Claude 3, OpenSearch | Awaiting next sprint | Frank Enendu
8 | Data Analyst Agent | P1 | Active | Low | 1 open (#19) | 2026-04-30 | Nothing done | - | FastAPI, Claude Agent SDK, LiteLLM | Build agentic harness (due Apr 30) | Frank Enendu
9 | AI R&D Tracker | P1 | Active/Internal | Low | 3 open (#3, #7, #9) | 2026-04-11 | N/A | - | Python, GitLab API | GitLab PAT fixed — resume sync | Frank Enendu
10 | Roadmap Intelligence | P2 | Active | Low | 0 (closed #17) | - | Nothing done | http://roadmap-mcp-dev-alb-*.eu-west-1.elb.amazonaws.com | FastAPI MCP, Jira API, Gemini | DNS & SSL setup | Frank Enendu
11 | Error Analysis Tool | P2 | In Progress | Low | 0 | - | Nothing done | https://d2lv9gmcz9m4c3.amplifyapp.com | Next.js 15.5, Lambda, DynamoDB | Continue development | Frank Enendu
12 | Tableau MCP Agent | P2 | Active | Low | 0 | - | Nothing done | - | Next.js, FastAPI, LangGraph | Continue development | Frank Enendu
13 | Video Analysis | P3 | Validation Phase | Low | 0 | - | N/A | - | Python, Gemini, Databricks | Validation pipeline | Frank Enendu
Due Date Legend: |  |  | OVERDUE | Due ≤3 days | On Track

## My GitLab Issues
FRANK'S OPEN GITLAB ISSUES — TASK TRACKER
Source: gitlab.ballys.tech/igaming/ai-rd/task-tracker ¦ Pulled: 2026-04-14 21:38
# | Issue | Project | Priority | Due Date | Status | Days Left | Action Required
#11 | Decompress Game Experience Dimensions 9→5/6 | Game Experience | P0 | 2026-04-16 | Open | 2 | Due very soon — prioritize today
#13 | Migrate Hackathon Platform to scalable infra | Hackathon Platform | P0 | 2026-04-17 | Open | 3 | Due this week
#30 | Review AI Engineer Conference Update | Conference | - | 2026-04-17 | Open | 3 | Due this week
#12 | Run Game Experience for full catalogue (Sunny list) | Game Experience | P0 | 2026-04-20 | Open | 6 | On track
#15 | Follow up R&D Prototype SSO/DNS for all prototypes | AI R&D Infra | P0 | 2026-04-20 | Open | 6 | On track
#14 | Get Hackathon Platform ready for Ignite Hackathon | Hackathon Platform | P0 | 2026-04-22 | Open | 8 | On track
#16 | Start brainstorming Portfolio Optimisation | Portfolio Optimisation | P0 | 2026-04-25 | Open | 11 | On track
#19 | Build Agentic Harness & Research Capability — Data Agent | Data Agent | P1 | 2026-04-30 | Open | 16 | On track
#29 | Review AI Code Review RFC | General | - | No date | Open | - | Set a due date
#7 | Test issue — sync validation | Task Tracker | P1 | 2026-04-11 | Open (overdue) | -3 | OVERDUE by 3 days!

## This Week
THIS WEEK — MEETINGS & DEADLINES
Date | Time | Event | Type | With | Notes
Mon Apr 14 | 08:00-09:00 | Hackathon Setup | Meeting | Al Jepps | Ignite hackathon prep
Mon Apr 14 | 13:00-13:45 | Qodo Code Review — Post Conference | Meeting | Qodo (David F), Al, Sunny | Follow-up from AI Eng conf
Mon Apr 14 | 15:30-16:00 | Communication Skills | Personal | - | Daily recurring
Wed Apr 16 | 09:30-10:00 | Skills Repo Promotion Plan | Meeting | Tomasz Borys | Brainstorm skills repo promotion
Wed Apr 16 | 15:30-16:00 | Monthly AI R&D Product Meeting | Meeting | Al, Craig, Nathan, Dez, Sunny | Demo AI R&D output + product feedback
Wed Apr 16 | 16:30-19:00 | Tech Meet Up — External Event | Event | Manchester office | External participants
Wed Apr 16 | - | DEADLINE: Game Experience dimensions (#11) | Deadline | - | P0 — Decompress 9→5/6
Thu Apr 17 | - | DEADLINE: Hackathon infra migration (#13) | Deadline | - | P0 — Scalable infrastructure
Thu Apr 17 | - | DEADLINE: Review conf update (#30) | Deadline | - | Assigned by Al
Mon Apr 20 | 08:30-09:00 | AI R&D Weekly Catchup | Meeting | Al, Sunny | Weekly standup
Mon Apr 20 | 09:00-09:30 | Manchester Weekly Update | Meeting | All Manchester | Domain project updates
Mon Apr 20 | - | DEADLINE: SSO/DNS follow-up (#15) | Deadline | - | P0 — All prototypes
Mon Apr 20 | - | DEADLINE: Game catalogue run (#12) | Deadline | - | P0 — Sunny list

## PIT Infrastructure
PIT INFRASTRUCTURE STATUS — EXTERNAL-FACING APPS
Application | Intended Domain | SSO | DNS | SSL Cert | My App
Hackathon Platform | hackathon.ballys.com | Done | Done | Done | NOT added
Capex Machine | capexmachine.ballys.tech | Done | Pending | Pending | N/A
Ballys Skills Repo | TBD | Pending | Ticket raised | Ticket raised | N/A
Game Experience | gameexperienceprofile.ballys.tech | Pending | Pending | Pending | N/A
Roadmap Intelligence | roadmapintelligence.ballys.tech | Pending | Pending | Pending | N/A
Error Analysis Tool | TBD | Pending | Pending | Pending | N/A

## Team Board
FULL TEAM BOARD — ALL OPEN GITLAB ISSUES
# | Title | Assignee | Project | Priority | Due Date | Labels
#25 | Record 10-min Adaptive Layouts video | Sudhanva | Adaptive Layouts | P0 | - | project::adaptive-layouts
#14 | Get Hackathon Platform ready for Ignite | Frank | Hackathon | P0 | 2026-04-22 | project::hackathon
#13 | Migrate Hackathon to scalable infra | Frank | Hackathon | P0 | 2026-04-17 | project::hackathon
#12 | Run Game Experience for full catalogue | Frank | Game Experience | P0 | 2026-04-20 | project::game-experience
#11 | Decompress Game Experience dimensions | Frank | Game Experience | P0 | 2026-04-16 | project::game-experience
#16 | Start brainstorming Portfolio Optimisation | Frank | Portfolio Opt. | P0 | 2026-04-25 | project::portfolio-opt.
#15 | Follow up SSO/DNS for all prototypes | Frank | AI R&D Infra | P0 | 2026-04-20 | project::ai-r&d-infra
#5 | Evaluate Harman Automated Game Testing Tool | Sudhanva | Harman | P0 | 2026-04-01 | project::harman
#2 | Set up clustering pipeline | Unassigned | Clustering | P0 | 2026-04-01 | project::clustering
#26 | Demo Contentful tagging system | Sudhanva | Adaptive Layouts | P1 | - | project::adaptive-layouts
#24 | Plan Adaptive Layouts agent sprint | Sudhanva | Adaptive Layouts | P1 | - | project::adaptive-layouts
#27 | GRA — access setup and experiment prep | Sudhanva | GRA | P1 | - | project::gra
#21 | Drudgery Audit — Own & Execute | Sudhanva | Automation Pillar | P1 | - | project::automation-pillar
#20 | AI Automation Pillar strategy | Sudhanva | Automation Pillar | P1 | - | project::automation-pillar
#19 | Build Agentic Harness — Data Agent | Frank | Data Agent | P1 | 2026-04-30 | project::data-agent
#4 | Dev Sizing Tool — remaining work | Sudhanva | Dev Sizing Tool | P1 | - | project::dev-sizing-tool
#30 | Review AI Eng Conference Update | Frank | Conference | - | 2026-04-17 | project::conference
#29 | Review AI Code Review RFC | Frank | General | - | - | project::general